## Addl Submtl Reqmts
Study Phase | 30% | 60% | 90% | 100% - FINAL
ü |  |  |  |  | Additional Submittal Requirements - STUDY AND ANALYSIS PHASE (NOT A FORMAL DRC SUBMITTAL)
Confer with project manager & review project objectives, requirements & criteria
Perform a field visit to visually inspect Project site
Perform reconnaissance surveys and utility location investigations
Review recorded as-built plans, surveys, and utility easement information
Conduct property ownership & plat research
Identify any necessary ROW & easement requirements for Supporting Documentation
Develop existing ROW & ownership maps
ADA curb ramp & driveway compliance review with concise tabular summary of findings
Identify permitting & approval agency requirements
Collect & review all available information affecting the project (from agencies, property owners, developers)
Coordinate project with stakeholders
Conduct public meeting with the city (as called for) – providing material & comments
Initiate traffic analyses as (as required)
Initiate/prepare NMDOT certification requirements (as required)
Develop the design decision matrix for the project
Update project schedule accordingly
Additional Submittal Requirements - 30% PLAN SUBMITTAL (NOT A FORMAL DRC SUBMITTAL)
| ü |  |  |  | Upon receiving authorization from the City to proceed:
Notify in writing all utility companies in the project area
-Provide plans for utility location mark ups if utility is impacted
Coordinate with utility companies in the area
Update the design decision matrix for the project
Complete 30% design plans following the latest PLAN SHEET SUBMITTAL CHECKLIST (attached)
-Submit reproducible 11” x 17” electronic PDF to City Project Manager
Create preliminary Engineer's Cost Estimate (30% Contingency & NMGRT)
Draft drainage memo (information to be incorporated in final drainage report)
Attend pre-design meeting
Coordinate the project with GAATC
Conduct public meeting with the city (as called for) – providing material & comments
Prepare NMDOT certification requirements (as required)
| ü |  |  |  | Supporting Documentation - 30% PLAN SUBMITTAL (NOT A FORMAL DRC SUBMITTAL)
Preliminary Drainage Report & Supporting Calculations
Exhibit Showing the Proposed Right of Way (Exclude area calculations from plans)
Preliminary Summary of Earthwork Quantities
Preliminary Submittal of Roadway Cross Sections at 50' Intervals
Preliminary Geotechnical Report
Preliminary Traffic Analysis (when applicable)
Preliminary Street Lighting Calculations (when applicable)
Additional Submittal Requirements - 60% PLAN SUBMITTAL (FORMAL DRC SUBMITTAL)
|  | ü |  |  | Upon receiving authorization from the City to proceed:
|  | ü |  |  | Build on Information Contained in 30% Plan Submittal
Prepare updated Engineer's Cost Estimate (20% Contingency & NMGRT)
Finalize real estate acquisition requirements (if included)
Perform sight distance analysis for intersections within project
Coordinate with GAATC
Public meeting with the City (as needed)
Update the design decision matrix for the project
Complete 60% design plans following the latest DMD Engineering PLAN SHEET SUBMITTAL CHECKLIST (attached)
-Incorporate comments from 30% review with Project Manager
-Submit cost estimate and reproducible 11"x17" electronic PDF of plans to City Project Manager
Submit reproducible 11"x17" electronic PDF and one (1) full size hard copy to DRC for review & comment
-Attend DRC meeting, provide summary of conclusions & updated design decision matrix
|  | ü |  |  | Supporting Documentation - 60% PLAN SUBMITTAL (NOT FORMAL DRC SUBMITTAL)
Prepare Contract Documents using standard City forms & format (at Discretion of PM)
1st Submittal of Project Specifications (Special Provisions)
Right of Way Title Reports on Property requiring new right of way (COA Responsibility)
Additional Submittal Requirements - 90% SUBMITTAL (FORMAL DRC SUBMITTAL)
|  |  | ü |  | Upon receiving authorization from the City to proceed:
|  |  | ü |  | Build on Information Contained in 60% Plan Submittal
Perform sight distance analysis for landscaping designs within project
Attend neighborhood meetings (as needed)
Prepare detailed take-off cost estimate (10% Contingency & NMGRT)
Prepare an estimate of time to construct the work
Update the design decision matrix for the project
Complete 90% design plans following the latest DMD Engineering PLAN SHEET SUBMITTAL CHECKLIST (attached)
-Incorporate comments from 60% review with Project Manager
-Submit cost estimate and reproducible 11"x17" electronic PDF of plans to City Project Manager
Submit reproducible 11"x17" electronic PDF and one (1) full size hard copy to DRC for review & comment
-Attend DRC meeting, provide summary of conclusions & updated design decision matrix
-Address all preliminary DRC comments not incorporated in writing
|  |  | ü |  | Supporting Documentation - 90% SUBMITTAL (NOT FORMAL DRC SUBMITTAL)
Final Drainage report with supporting calculations (to go to Hydrology for review)
Pre-final Project Specifications (to go to legal for review)
Pre-final Engineer's Estimate and Quantities (10% Contingency & NMGRT)
Final Summary of Earthwork Quantities
Final Geotechnical Report
2nd Submittal of Roadway Cross Sections at 50' Intervals
Final R/W and Easement Requirements with Legal Descriptions and Exhibits
Additional Submittal Requirements - 100% - FINAL SUBMITTAL (FORMAL DRC SUBMITTAL)
|  |  |  | ü | Upon receiving authorization from the City to proceed:
|  |  |  | ü | Build on Information Contained in 90% Plan Submittal
Provide Construction Documents in the following order:
Supporting Documentation
Specifications/Contract Documents Final Estimate, Quantities, Bid Form
Complete final 100% design plans following the latest DMD Engineering PLAN SHEET SUBMITTAL CHECKLIST (attached)
-Incorporate comments from 90% review with Project Manager
-Submit reproducible 11” x 17” electronic PDF to City Project Manager
Submit final signed and stamped reproducible 11” x 17” electronic PDF to DRC to be routed electronically for signature.

## Plan Sheet Sequence
30% | 60% | 90% | 100% - FINAL | Plan Sheet Sequence (Numbering of sheets - 1-1, 2-1, 3-1, 3-1A, etc.) | Shaded indicates not needed that phase
General – 1- Series
Title or Cover Sheet
Logo – City black and white logo
Logo – Federal/State as needed
Vicinity Map - Top right corner of page (4”x4”, 1:500 or 1:1000 scale)
Description of the nature of the work proposed (Place under vicinity map)
Length of project
Index of Sheets
Sheet frames & stationing overview
General Notes
Plan sheet legend
Estimated Quantities
List categories and items
Include estimated and final quantity columns
Quantity Schedules (at discretion of City PM)
Removals
Typical Sections
Existing
Show lane widths
Existing surfacing/pavement design
Cross-slopes
Stationing
Proposed
Show lane widths
Proposed surfacing/pavement design
Cross-slopes
Construction centerline
Stationing
BOP and EOP
Traffic Design Criteria - Traffic Count Design Information
Design speed
Traffic volumes
SWPPP Information Sheet
Erosion and Sediment Control Plan (Temporary/During Construction)
Environmental Sheet (Only use when using federal funds)
ROW Details – 2 Series
Existing Right of Way Line Work (1:100 or 1:200 scale)
Proposed Right of Way Line Work (1:100 or 1:200 scale)
ROW Mapping per DOT Standards (Federal funding)
ROW Details (show TCP’s, TCE’s, CME’s, boundaries, acquisitions) (1:20 scale)
Stations and locations
Roadway Details – 3 Series
Survey and Control Points (with bearing & distance indicated for tie-in)
Plan and Profile Sheets
Intersection Details
Curb Ramp Details (indicate widths with 1/4 points, flow line elevations)
Driveway Details and Profiles (indicate widths with 1/4 points, flow line elevations)
Structures – 4 Series
Structural Details (Including limits and profiles)
Traffic Details – 5 Series
Signing and Pavement Layouts (Include visual representation and designation of placed signs)
Show proposed sign layouts
Show proposed striping layouts (show lane widths)
Provide summary sheet providing schedules including item description and quantities
Traffic Signal Layouts
Show proposed plan & approach (elev.) view of mast arm, pedestal, controllers and service connection (include PNM contact)
Provide summary sheet providing schedules including item description and quantities
Phasing and timing
Detection details
ITS layouts
Illumination
Show proposed plan for lighting, controllers and service connection (include PNM contact)
Show lighting design parameters, voltage drops, and load calculations
Provide summary sheet providing schedules including item description and quantities
Drainage Details – 6 Series
Plan and Profile Sheets (Include HGL)
Show pot hole locations in plan and profile views
Include pot hole tables (Northing, Easting, depth, size, type/material)
Hydraulic/Hydrologic Details
Show drop inlets, median drains, manholes, etc
Provide summary sheet providing schedules including item description and quantities
Grate Details
Erosion and Sediment Control Plan (Permanent/Post-Construction)
Utility Sheets – 7 Series
Utility Sheets
Plan and profile sheets (SUE level D, C, B; Identify potential conflicts)
Pot hole locations (horizontal, SUE level A)
Landscaping Details – 8 Series
Irrigation Plans and Details
Irrigation line layouts, etc.
Landscaping Plans and Details
Plantings
Traffic Control Plan – 9 Series
Traffic Control Plan Sheet (Only use with federal funding)
Green Stormwater Infrastructure (GSI) Sheets – Series TBD by Planning
GSI Sheets
Plan and profile sheets
Detail Sheets

## old guidelines (hidden)
Guidelines from old version Submittal Requirements Checklist
30%
Cover Sheet with Project Information & Vicinity Map Tentative Sheet Index
General Notes Sheet
Roadway Geometrics (Including Intersections)
Initial Typical Roadway Sections & Preliminary Pavement Structural Sections Initial Roadway Plan and Profile Sheets
Location of Existing Utilities (Plan View) Proposed and Existing Right of Way Proposed Grading Limits
Existing Contours (Shaded back on Plan & Profile Sheets) Proposed Roadway Striping
Include in General the Appropriate Labels, Dimensions, & Stationing Location & Preliminary Size of Proposed Drainage Structures
60%
Identification of Util. Conflicts & New Util. Installations in Plan and Profile
Location of Existing Utilities
Proposed and Existing Right of Way (Dimensioned)
1st Submittal of Signal Plans (layout)
1st Submittal of Landscape/Irrigation Plans (layout)
1st Submittal of Intersection Design Sheets
1st Submittal of Plan and Profile of Storm Drain
1st Submittal of Profiles of Catch Basins and Connector Pipes
1st Submittal of Median Details
1st Submittal of Roadway Signing & Striping
1st Submittal of Removal Sheets
Supporting Documentation
Preliminary Drainage Report & Supporting Calculations
Exhibit Showing the Proposed Right of Way
1st Submittal of Project Specifications (Special Provisions)
Preliminary Engineer's Cost Estimate and Quantities (20% Contingency)
Preliminary Summary of Earthwork Quantities
Right of Way Title Reports on Property requiring new right of way (to be obtained after the 60% review by DRC)
Preliminary Submittal of Roadway Cross Sections at 50' Intervals
Preliminary Geotechnical Report
Preliminary Traffic Analysis (when applicable)
Preliminary Street Lighting Calculations (when applicable)
90%
Final Resolution of Util. Conflicts in plan and profile
Pre-Final Plans of Util. Relocations
Pre-Final Plans for Util. Installations
Pre-final Intersection Design Sheets
Pre-final Plan and Profile of Storm Drain
Pre-final Profiles of Catch Basins and Connector Pipes
Pre-final Roadway Signing & Striping Plans
Pre-final Signal Plans Pre-final Lighting Plans
Pre-final Landscape/Irrigation Plans
Pre-final Special Details
Pre-final Erosion Control Plans and Details (optional)

## Sheet1 (hidden)
2015-12-15
STUDY AND ANALYSIS PHASE (NOT A FORMAL DRC SUBMITTAL)
Confer with project manager & review project objectives, requirements & criteria
Perform a field visit to visually inspect Project site
Perform reconnaissance surveys and utility location investigations
ADA curb ramp & driveway compliance review with concise tabular summary of findings
Identify permitting & approval agency requirements
Collect & review all available information affecting the project
-from agencies, property owners, developers
Coordinate project with stakeholders
Review recorded as-built plans, surveys, and utility easement information
Conduct property ownership & plat research
Identify any necessary ROW & easement requirements
Develop existing ROW & ownership maps
Conduct public meeting with the city (as called for) – providing material & comments
Initiate traffic analyses as (as required)
Initiate/prepare NMDOT certification requirements (as required)
Develop the design decision matrix for the project
Update project schedule accordingly
30% PLAN SUBMITTAL (NOT A FORMAL DRC SUBMITTAL)
Upon receiving authorization from the City to proceed:
Notify in writing all utility companies in the project area
-Provide plans for utility location mark ups if utility is impacted
Complete 30% design plans following the latest DMD Engineering Plan Sheet Sequence
-Submit reproducible 11” x 17” electronic PDF to City Project Manager
Create preliminary Engineer's Cost Estimate (with 30% Contingency)
Draft drainage memo (information to be incorporated in final drainage report)
Attend pre-design meeting
Coordinate the project with GABAC & GARTC
60% PLAN SUBMITTAL (FORMAL DRC SUBMITTAL)
Upon receiving authorization from the City to proceed:
Build on Information Contained in 30% Plan Submittal
Coordinate with utility companies in the area
Prepare updated Engineer's Cost Estimate (with gross receipts tax & 20% Contingency)
Finalize real estate acquisition requirements (if included)
Coordinate with GABAC & GARTC
Public meeting with the City (as needed)
Attend DRC meeting, provide summary of conclusions & updated design decision matrix
Complete 60% design plans following the latest DMD Engineering Plan Sheet Sequence
-Incorporate comments from 30% review with Project Manager
-Submit reproducible 11” x 17” electronic PDF to City Project Manager
Drawing sheets meet the latest DMD Engineering standard guidelines (v.1215)
Supporting Documentation
Preliminary Drainage Report & Supporting Calculations
Exhibit Showing the Proposed Right of Way
1st Submittal of Project Specifications (Special Provisions)
Preliminary Summary of Earthwork Quantities
Right of Way Title Reports on Property requiring new right of way (to be obtained after the 60% review by DRC)
Preliminary Submittal of Roadway Cross Sections at 50' Intervals
Preliminary Geotechnical Report
Preliminary Traffic Analysis (when applicable)
Preliminary Street Lighting Calculations (when applicable)
90% SUBMITTAL (FORMAL DRC SUBMITTAL)
Upon receiving authorization from the City to proceed:
Build on Information Contained in 60% Submittal
Prepare 90% design plans incorporating comments from 60% review
Prepare complete Contract Documents using standard City forms & format
Attend neighborhood meetings (as needed)
Prepare detailed take-off cost estimate with 10% contingency & NM gross receipts tax
Prepare an estimate of time to construct the work
Submit plans and cost estimate to DRC for review & comment
-Address all preliminary DRC comments not incorporated in writing
Supporting Documentation
Final Drainage report with supporting calculations
Pre-final Project Specifications (to go to legal for review)
Pre-final Engineer's Estimate and Quantities (10% Contingency)
Final Summary of Earthwork Quantities
Final Geotechnical Report
2nd Submittal of Roadway Cross Sections at 50' Intervals
Final R/W and Easement Requirements with Legal Descriptions and Exhibits
100% - FINAL SUBMITTAL (FORMAL DRC SUBMITTAL)
Construction Documents in the following order:
Supporting Documentation
Specifications/Contract Documents Final Estimate, Quantities, Bid Form
Deliverables: Three (3) copies of true half size plans (11"xl7") and a PDF document for all project plans
and supporting documentation. All submittals made to DRC will follow the DRC requirements; this
should be coordinated with the City Project Manager.
Study Phase, 30%, 60%, 9 0%, 1 00%-FINAL
MINIMUM PROJECT SUBMITTAL REQUIREMENTS
FOR ROADWAY IMPROVEMENTS